## Sheet1
Generic NIH Research Grant (R01/R21/R03) Timeline & Checklist |  |  | Blue = Complete | Red = incomplete
*Review the current NIH guidelines for the specific opportunity you are applying to, and update this checklist as needed.
Then update the timeline and dates to fit your schedule.
| NOTES | RESPONSIBILITY | T-12 WEEKS | T-10 WEEKS | T-8 WEEKS | T-6 WEEKS | T-4 WEEKS | T-3 WEEKS | T-2 WEEKS | T-1 WEEKS | UGA Internal DEADLINE | NIH DEADLINE
|  |  | [date] | [date] | [date] | [date] | [date] | [date] | [date] | [date] | [date - typically 4-5 business days prior to NIH deadline] | [date]
Create in UGA Grants Portal |  | SPA/DLSA | Draft | [7 empty] | Final
Grants.gov/SF424 Forms |  | SPA/DLSA | Start | [5 empty] | Finalize
Proposal Title |  | PI | Draft | Final | [6 empty] | Final
Project Summary | 30 lines of text, for the scientifically literate lay reader | PI |  |  |  | Draft |  | Complete Draft to OPE | Revised Draft | Final Draft | Final
Project Narrative | 3 sentences; public health relevance statement | PI |  |  |  | Draft |  | Complete Draft to OPE | Revised Draft | Final Draft | Final
Specific Aims | 1 page | PI |  | Draft |  |  | Revised/Final Draft to OPE |  |  | Final Draft | Final
Research Strategy | No URLs or hyperlinks permitted. Review your FOA to verify page limit. R01s - typically 12 page limit. R21s - typically 6 page limit. Requires the below 3 sections. Refer to your FOA for FOA-specific requirements. | PI | Outline | Beefy Outline | Draft with Holes |  | Complete Draft |  |  | Final Draft | Final
Significance
Innovation
Approach
Bibliography | No page limit; No URLs or hyperlinks permitted. | PI |  |  |  | Draft |  |  |  | Final Draft | Final
Facilities and Other Resources | No page limit; No URLs or hyperlinks permitted. | PI |  |  |  | Draft |  |  | Revised Draft | Final Draft | Final
Equipment | No page limit; No URLs or hyperlinks permitted. | PI |  |  |  | Draft |  |  | Revised Draft | Final Draft | Final
Resource Sharing Plan | Review FOA to determine need. | PI | [5 empty] | Draft | Revised Draft | Final Draft | Final
Data Management & Sharing Plan | See new instructions on DMSP requirements. https://sharing.nih.gov/data-management-and-sharing-policy/planning-and-budgeting-for-data-management-and-sharing/writing-a-data-management-and-sharing-plan#elements-to-include-in-a-data-management-and-sharing-plan | PI | [5 empty] | Draft | Revised Draft | Final Draft | Final
Biosketches - Key Personnel | Required for all Key Personnel. 5 page limit per biosketch. | PI | Identify Personnel | Request |  |  |  | Receive |  | Complete | Final
Budget | Review your specific FOA to verify which budget forms are allowed for your application. You will either prepare a Modular or Detailed budget for NIH, but will still prepare a detailed budget for UGA. | PI & DLSA |  |  | Initial Draft |  | Revised Draft |  | Final Draft |  | Final
Budget Justification | Review your specific FOA to verify which budget justification information you need to provide. There are different requirements for a budget justification to accompany a Modular versus Detailed budget. | PI |  |  | Initial Draft |  | Revised Draft |  | Final Draft |  | Final
Letters of Support and Consultant Letters | Optional | PI |  | Identify Need, and Identify Collaborators | Request |  | Receive |  |  |  | Final
Subaward Documentation | Only required if the project includes subawards. Required documents include: Biosketches for Key Personnel; Subaward budget; Subaward Budget justification; Scope of Work. Review your FOA for FOA-specific requirements, and consult with your DLSA/SPA. | PI/SPA/DLSA |  | Identify Subawards | Request Subaward documents |  |  | Receive |  |  | Final
Human Subjects and Clinical Trials Information | Only required for projects involving human subjects. See https://humansubjects.nih.gov/ | PI |  | Identify Need |  | Draft |  |  | Final Draft |  | Final
Vertebrate Animals Attachment | Only required for projects involving vertebrate animals research. | PI |  | Identify Need |  | Draft |  |  | Final Draft |  | Final
Select Agent Research | Only required for projects involving use of select agents. | PI |  | Identify Need |  | Draft |  |  | Final Draft |  | Final
Multiple PI Leadership Plan | Only required for projects with more than 1 PI | PI |  | Identify Need |  |  |  | Draft |  | Final Draft | Final
Authentication of Key Biological and/or Chemical Resources | 1 page suggested limit. | PI |  | Identify Need |  |  |  | Draft |  | Final Draft | Final
Appendix | Review FOA to determine if there are any special appendix instructions for your application. | PI |  | Identify Need |  | Draft |  |  | Final Draft |  | Final
PHS Assignment Request Form | Optional | PI | [5 empty] | Identify Need |  | Complete | Final
Submission to SPA/DLSA |  | PI | [8 empty] | Send to SPA
Submission by SPA/DLSA to NIH |  | SPA/DLSA | [9 empty] | Submit to NSF