## Sheet1
| Responsibility | [10 empty] | UGA DEADLINE | USDA DEADLINE
|  | Notes | 2017-04-18 | 2017-04-25 | 2017-05-02 | 2017-05-09 | 2017-05-16 | 2017-05-23 | 2017-05-30 | 2017-06-07 | 2017-06-14 | 2017-06-21 | 2017-06-28
Meetings |  | Optional; depends on desired work process | 2017-04-18: Kick-off; 2017-05-09: Budget; 2017-05-23: Check-in; 2017-05-30: Check-in; 2017-06-07: Check-in; 2017-06-14: Check-in
UGA Transmittal Form |  | Internal form that collects data; also used for routing for approvals (PIs, Dept. Head, Dean) | 2017-04-25: Draft; 2017-06-14: Complete; 2017-06-21: Route
SF 424 R&R Form |  | This mostly autofills. | 2017-05-09: Draft; 2017-06-21: Final
R&R Performance Site Location Form |  | This autofills for UGA; add locations for additional sites | 2017-05-09: Draft; 2017-06-21: Final
R&R Other Project Information Form |  |  | 2017-05-09: Draft; 2017-06-21: Final
7) Project Summary/Abstract |  | https://nifa.usda.gov/resource/application-support-templates The summary should also include the relevance of the project to the goals of the Program Area Priority within this RFA to which the application is submitted. See RFA, p.63; NIFA Grants.gov instructions, p.33 | 2017-04-18: Draft; 2017-05-30: Revised Draft; 2017-06-14: Proofread, Finalize; 2017-06-21: Final
8) Project Narrative |  | Project Narrative section may not exceed a total of 18 pages with 12-point font and line spacing not exceeding six lines of text per vertical inch, including all figures and tables. | 2017-05-02: Outline; 2017-05-16: Draft for Circulation; 2017-05-30: Revised Draft; 2017-06-14: Proofread, Finalize; 2017-06-21: Final
(a) Introduction |  | See RFA, pp. 64-65 | bar: 2017-05-02; 2017-05-16; 2017-05-30; 2017-06-14
(b) Rationale and Significance |  | See RFA, pp. 64-65 | bar: 2017-05-02; 2017-05-16; 2017-05-30; 2017-06-14
(c) Approach |  | See RFA, pp. 64-65 | bar: 2017-05-02; 2017-05-16; 2017-05-30; 2017-06-14
9) Bibliography & References Cited |  | See RFA, p.69 | 2017-06-21: Final
10) Facilities & Other Resources |  | See RFA, p.69; Cf. NIFA Grants.gov instructions, p.33 | 2017-05-23: Draft; 2017-06-21: Final
11) Equipment |  | See RFA, p.69 | 2017-05-23: Draft; 2017-06-21: Final
12) Other Attachments |  |  | 2017-06-21: Final
1) Key Personnel Roles |  | 2 page limit. | 2017-05-23: Draft; 2017-06-21: Final
2) Logic Model |  | 2 page limit. Optional but encouraged for Research proposals. https://nifa.usda.gov/resource/integrated-programs-logic-model-planning-process | 2017-05-23: Draft; 2017-06-21: Final
3) Management Plan |  | 3 page limit. Optional but encouraged for Research proposals. See RFA, p.70 | 2017-05-23: Draft; 2017-06-21: Final
4) Data Management Plan |  | 2 page limit. Required for Research proposals. | 2017-05-23: Draft; 2017-06-21: Final
a. Expected Data Type |  | See RFA, pp. 70-71 for instructions | 2017-06-21: Final
b. Data Format |  |  | 2017-06-21: Final
c. Data Storage and Preservation |  |  | 2017-06-21: Final
d. Data Sharing and Public Access |  |  | 2017-06-21: Final
e. Roles and Responsibilities |  |  | 2017-06-21: Final
5) Documentation of Collaboration |  | No page limit. Letters of support showing that collaborators involved have agreed to render services. | 2017-04-18: Finalize; 2017-05-09: Solicit; 2017-05-30: Deadline; 2017-06-21: Final
6) Preprints |  | Optional. Limited to 2 preprints. See RFA, p. 72 | 2017-06-21: Final
8) Felony Convictions/Tax Delinquent Status |  | https://nifa.usda.gov/resource/application-support-templates Your grants administrator can help with this form. | 2017-06-21: Final
R&R Senior/Key Person Profile |  |  | 2017-06-21: Final
*Biographical Sketch |  | 2-page limit. Use OLD NSF format with NIFA requirements for publications; See NIFA Grants.gov instructions, p.36-37 | 2017-04-25: Solicit; 2017-05-16: Deadline; 2017-05-23: Request revisions; 2017-06-21: Final
*Current & Pending Support |  | https://nifa.usda.gov/resource/application-support-templates Only required for PD and Co-PDs. | 2017-04-25: Solicit; 2017-05-16: Deadline; 2017-05-23: Request revisions; 2017-06-21: Final
R&R Personal Data |  | Optional demographic info. | 2017-06-21: Final
R&R Budget Form |  | Max $500k for project including F&A costs. See NIFA Grants.gov instructions, p.39-46 | 2017-06-21: Final
*Internal Budget Spreadsheet |  |  | 2017-05-09: Draft; 2017-05-30: Revised; 2017-06-14: Finalize; 2017-06-21: Final
*Budget Justification |  | No page limit. See RFA, p. 76 | 2017-05-16: Draft; 2017-06-07: Revised; 2017-06-14: Finalize; 2017-06-21: Final
NIFA Supplemental Information Form |  |  | 2017-06-21: Final
*Conflict of Interest List |  | https://nifa.usda.gov/resource/application-support-templates | 2017-04-25: Solicit; 2017-06-21: Final
Submission to SPA | bar: 2017-06-21
Submission by SPA to USDA | bar: 2017-06-28
NIFA GRANTS.GOV INSTRUCTIONS:
https://apply07.grants.gov/apply/opportunities/instructions/oppUSDA-NIFA-EXCA-005297-cfda10.500-instructions.pdf