## Sheet1
Checklist and Suggested Timeline for NSF CAREER Grants |  | pink=incomplete | blue=complete
NSF CAREER Program Solicitation (22-586) |  | T-12 weeks | T-10 weeks | T-8 weeks | T-7 weeks | T-6 weeks | T-5 weeks | T-4 weeks | T-3 weeks | T-2 weeks | T-1week | UGA DEADLINE | NSF DEADLINE
| Notes | 2025-04-30 | 2025-05-14 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-07-16 | 2025-07-17 | 2025-07-23
Suggested Reviewers (opt) | https://new.nsf.gov/policies/pappg/24-1/ch-2-proposal-preparation#ch2D1b | 2025-07-16: Complete; 2025-07-17: Final
Cover Sheet | https://new.nsf.gov/policies/pappg/24-1/ch-2-proposal-preparation#ch2D2a | 2025-05-14: Start proposal in Research.gov and allow SRO view/edit access; 2025-07-16: Complete; 2025-07-17: Final
Project Summary | 1 page (upload to check) https://new.nsf.gov/policies/pappg/24-1/ch-2-proposal-preparation#ch2D2b | 2025-06-25: Draft; 2025-07-17: Final
Project Description | 15 pages. URLs are not allowed. Must include a separate section for Broader Impacts. If applicable, include Prior NSF Support. https://new.nsf.gov/policies/pappg/24-1/ch-2-proposal-preparation#ch2D2d | 2025-04-30: Beefy Outline; 2025-05-28: Draft with Holes; 2025-06-11: Complete Draft to Peers; 2025-06-25: Revised Draft to OPE; 2025-07-16: Final draft; 2025-07-17: Final
References | No page limit specified in PAPPG. https://new.nsf.gov/policies/pappg/24-1/ch-2-proposal-preparation#ch2D2e | 2025-06-11: Draft; 2025-07-16: Complete; 2025-07-17: Final
PERSONNEL DOCUMENTS
Biographical Sketches | 3 pages. Needed for PI, co-PIs, and senior personnel. Optional for other personnel. Biosketches for other personnel should be combined and uploaded as a single PDF as an Other Supplementary Document. Basic biosketch instructions from the PAPPG are here: https://new.nsf.gov/policies/pappg/24-1/ch-2-proposal-preparation#ch2D2hi Prepare document on SciENcv (Science Experts Network Curriculum Vitae) website: https://www.ncbi.nlm.nih.gov/sciencv/ | 2025-06-18: Draft; 2025-07-17: Final
Collaborators & Affiliations | https://new.nsf.gov/policies/pappg/24-1/ch-2-proposal-preparation#ch2D2hiii Link to template: https://nsf.gov/bfa/dias/policy/coa.jsp | 2025-07-16: Complete; 2025-07-17: Final
Current & Pending Support | Needed for PI, co-PIs, and senior personnel. The C&P is now part of the SciENcv form. Prepare/update it at https://www.ncbi.nlm.nih.gov/sciencv/ Basic C&P instructions from the PAPPG are here: https://www.nsf.gov/policies/pappg/24-1/ch-2-proposal-preparation#ch2D2hii | 2025-07-02: Draft; 2025-07-16: Complete; 2025-07-17: Final
Synergistic Activities | one page max A list of up to five distinct examples that demonstrates the broader impact of the individual’s professional and scholarly activities that focus on the integration and transfer of knowledge as well as its creation. See PAPPG for examples: https://new.nsf.gov/policies/pappg/24-1/ch-2-proposal-preparation#ch2D2hiv | 2025-06-18: Draft; 2025-07-09: Complete; 2025-07-17: Final
Other Personnel information (opt/if applicable) | Biosketches for other personnel should be combined and uploaded as a single PDF as an Other Supplementary Document. Per the PAPPG, they can be freeform rather than in the format required for senior personnel: https://new.nsf.gov/policies/pappg/24-1/ch-2-proposal-preparation#ch2D2hib | 2025-05-28: Identify other personnel; 2025-06-25: Request Biosketches; 2025-07-17: Final
Budget | https://new.nsf.gov/policies/pappg/24-1/ch-2-proposal-preparation#ch2D2f | 2025-06-04: Early Draft; 2025-06-25: Draft; 2025-07-17: Final
Budget Justification | 5 pages (also for subawards, if applicable) | 2025-06-25: Draft; 2025-07-17: Final
Facilities, Equipment & Other Resources | No page limit This is an aggregated description that includes both physical and personnel resources. It includes resources collaborators will provide and resources accessed through unfunded collaborations. https://new.nsf.gov/policies/pappg/24-1/ch-2-proposal-preparation#ch2D2g | 2025-06-25: Draft; 2025-07-17: Final
Data Management Plan | Required. 2 pages. See guidance from UGA Libraries: https://researchdata.uga.edu/services/datamanagement Use your UGA credentials for dmptool.org. https://new.nsf.gov/policies/pappg/24-1/ch-2-proposal-preparation#ch2D2i-ii | 2025-07-09: Draft; 2025-07-17: Final
Departmental Letter | 2 pages max * Affirms investigator's early-career, pre-tenure status; * Affirms that proposed PI's CAREER resarch and education activities are supported by and advance departmental and organizational goals. * Describes relationship between the CAREER project, the PI's career goals and job responsibilities, and the departmental/organizational mission and how the department head (or equivalent) will ensure the appropriate mentoring of the PI. The Department Letter should not be construed as a Letter of Support for the PI and should address only the items listed above. | 2025-07-02: Request; 2025-07-16: Receive; 2025-07-17: Final
Letters of Collaboration | For substantial collaboration not included in the budget. Specific solicitations often provide further detail on required letters. Specific language is often required. Letters of collaboration are permitted, but letters of support are not permitted unless outlined in solicitation. https://new.nsf.gov/policies/pappg/24-1/ch-2-proposal-preparation#ch2D2i-iii | 2025-05-28: Have all collaborators identified; 2025-06-18: Have all collaborators confirmed; 2025-06-25: Send template to collaborators; 2025-07-09: Receive; 2025-07-17: Final
Supplementary Docs | https://new.nsf.gov/policies/pappg/24-1/ch-2-proposal-preparation#ch2D2i | 2025-07-09: Draft; 2025-07-17: Final
All Research.gov Components |  | 2025-07-17: Final Review
Submission to SPA/DLSA
Submission by SPA to NSF