## Sheet1
Starter Checklist and Suggested Timeline for NSF Grants
Check your program solicitation for full submission instructions. Many NSF programs require additional or modified components for full submission. This checklist serves as a starting point.
|  | T-8 WEEKS | T-6 WEEKS | T-4 WEEKS | T-3 WEEKS | T-2 WEEKS | T-1 WEEK | T-2 DAYS | UGA DEADLINE | NSF DEADLINE
| Notes | [date] | [date] | [date] | [date] | [date] | [date] | [date] | [date] | [date]
Suggested Reviewers (opt) | https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D1b | [6 empty] | Complete | Final
Collaborators & Affiliations | Needed for PI, co-PIs, and senior personnel. https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2hiii Link to template: https://nsf.gov/bfa/dias/policy/coa.jsp |  |  | Request |  |  | Receive (and combine) |  | Final
Cover Sheet | https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2a |  |  |  |  | Complete |  |  | Final
Project Summary | 1 page (upload to check) https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2b | Draft | [6 empty] | Final
Project Description | 15 pages. URLs are not allowed. Must include a separate section for Broader Impacts. If applicable, include Prior NSF Support. https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2d | Beefy Outline | Draft with Holes | Complete Rough Draft | Send 1st revision for review |  | Final draft |  | Final
References | No page limit specified in PAPPG. https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2e | [6 empty] | Complete | Final
Biographical Sketches | 3 pages. Needed for PI, co-PIs, and senior personnel. Optional for other personnel. Biosketches for other personnel should be combined and uploaded as a single PDF as an Other Supplementary Document. Note: The mandate to use SciENcv only for preparation of the biographical sketch will go into effect for new proposals submitted or due on or after October 23, 2023. In the interim, proposers may continue to prepare and submit this document via use of SciENcv or the NSF fillable PDF. NSF, however, encourages the community to use SciENcv prior to the October 2023 implementation. Basic biosketch instructions from the PAPPG are here: https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2hi | Have all personnel identified | Have all personnel confirmed | Request |  |  |  |  | Final
Other Personnel information (opt/if applicable) | Biosketches for other personnel should be combined and uploaded as a single PDF as an Other Supplementary Document. Per the PAPPG, they can be freeform rather than in the format required for senior personnel: https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2hib | [7 empty] | Final
Budget | https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2f | Early budget meeting | Follow-up budget meeting | Full draft |  | Review |  | Complete | Final
Budget Justification | 5 pages (also for Subawards) https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2f |  |  | Full draft |  | Review |  | Complete | Final
Subaward budget(s) and budget justification(s) (if applicable) | A separate budget and a budget justification of no more than five pages, must be provided for each subrecipient, if already identified. The description of the work to be performed must be included in the project description. https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2fvie | Have all subawards identified | Have all subawards confirmed | Begin subaward process with your SPA representative, DLSA, or Grants Coordinator |  | Finalize all subaward documentation |  |  | Final
Current & Pending Support | Needed for PI, co-PIs, and senior personnel. https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2hii |  |  | Request |  |  | Receive | Complete | Final
Facilities, Equip, Other | This is an aggregated description that includes both physical and personnel resources. It includes resources collaborators will provide and resources accessed through unfunded collaborations. No page limit specified in PAPPG. https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2g |  |  | Request |  |  | Receive (and combine) |  | Final
Special Information and Supplementary Documentation: | Overview: https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2i | [7 empty] | Final
Postdoc Mentoring Plan (if required) | Required if postdoc support is requested. 1 page. https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2i-i | [7 empty] | Final
Data Management Plan | Required. 2 pages. https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2i-ii | [5 empty] | Complete |  | Final
Off Campus Performance | If applicable. https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2i-iii | [7 empty] | Final
Letters of Collaboration | For substantial collaboration not included in the budget. Specific solicitations often provide further detail on required letters. Specific language is often required. Letters of collaboration are permitted, but letters of support are not permitted unless outlined in solicitation. https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2i-iv | Have all collaborators identified | Have all collaborators confirmed | Request |  | Receive |  |  | Final
International Activities | If applicable. https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2E8 | [7 empty] | Final
Environmental Impact Information | If applicable, NSF may request after proposal is submitted. https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2i-v | [7 empty] | Final
Antarctic Proposals | If applicable. https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2i-vi | [7 empty] | Final
Research in Historic Places | If applicable. https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2i-vii | [7 empty] | Final
Field Experiments with Genetically Engineered Organisms | If applicable. https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2i-viii | [7 empty] | Final
Documentation regarding Human Subjects, Hazardous Materials, Vertebrate Animals, or Endangered Species | If applicable. https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2i-ix | [7 empty] | Final
Other Special Information (if applicable) | https://new.nsf.gov/policies/pappg/23-1/ch-2-proposal-preparation#2D2i | [7 empty] | Final
All Fastlane Components | [8 empty] | Final Review
Submission to SPA
Submission by SPA to NSF